# Monitoring & Evaluation System: Reducing Early Marriages in Budalangi

## 1. Introduction

Early marriage remains a significant challenge in Budalangi, leading to adverse outcomes for girls, including limited education, poor health, and economic dependency. This M&E system is designed to guide the project team in systematically collecting, analysing, and using data to assess progress and make informed decisions.

## 2. M&E Objectives

- Monitor implementation progress of the intervention activities.

- Evaluate the effectiveness, efficiency, and impact of project strategies.

- Ensure accountability to donors, stakeholders, and beneficiaries.

- Generate learning for replication and policy influence.

## 3. Theory of Change

Goal: Reduce the prevalence of early marriages among girls aged 10–17 in Budalangi Constituency by 40% over two years.

Outcomes:

- Improved awareness of early marriage risks among community members.

- Increased school retention rates for girls.

- Strengthened enforcement of child protection laws.

- Empowered girls and families with economic and social alternatives.

Outputs:

- Community sensitization campaigns conducted.

- Schools supported with retention incentives.

- Trainings provided to local leaders, teachers, and parents.

- Girls’ mentorship and life skills sessions delivered.

## 4. Indicators Framework

| Level | Indicator | Means of Verification | Frequency |
| --- | --- | --- | --- |
| Impact | % reduction in early marriage rates | Baseline/endline surveys, MoH records | Annually |
| Outcome 1 | % of parents aware of early marriage risks | KAP surveys, FGDs | Bi-annually |
| Outcome 2 | School attendance rates for girls (10–17) | School records | Quarterly |
| Outcome 3 | # of reported and acted-upon child marriage cases | Police/Chief reports | Quarterly |
| Output 1 | # of community forums held | Activity 1.1 - Reports | Monthly |
| Output 2 | # of girls mentored | Activity 2.1 2.1.1 Attendance registers Activity 3.1 | Monthly |
| Output 3 | # of teachers/elders trained | 3.1.1 Training reports | Quarterly |

## 5. Data Collection Tools

- Baseline & Endline Surveys

- Knowledge, Attitudes and Practices (KAP) Questionnaires

- Focus Group Discussion (FGD) Guides

- School Attendance Registers

- Training & Activity Registers

- Case Monitoring Forms

## 6. Roles and Responsibilities

| Role | Responsibility |
| --- | --- |
| M&E Officer | Lead data collection, analysis, and reporting |
| Field Officers | Conduct community-level monitoring and documentation |
| Project Manager | Use M&E findings for planning and strategy |
| Partner Organizations | Provide data and support validation |
| Community Leaders | Participate in participatory monitoring |

## 7. Reporting & Learning

- Monthly Monitoring Reports

- Quarterly Progress Reviews

- Annual Evaluation Reports

- Learning Workshops to discuss challenges and insights

- Feedback Loops to community and stakeholders

## 8. Evaluation Plan

- Midterm Evaluation (Month 18): Assess project effectiveness and recommend course corrections.

- Endline Evaluation (Month 24): Measure overall project impact and sustainability.

Methods:

- Mixed-methods approach (quantitative surveys + qualitative interviews)

- Gender-sensitive and youth-inclusive evaluation tools

## 9. Data Quality Assurance

- Standardized tools and training for data collectors

- Regular supervision and field data audits

- Double data entry and verification protocols

- Storage in a secure, password-protected M&E database

## 10. Budgeting for M&E

Allocate 8–10% of total project budget for:

- Tool development

- Training and supervision

- Field data collection and validation

- Data analysis software/tools

- External evaluations

## 11. Logical Framework

| Objectives | Indicators | Means of Verification | Assumptions |
| --- | --- | --- | --- |
| Goal | 40% reduction in early marriages by 31st December 2026 | National statistics, Endline Survey | Continued political and community support |
| Outcomes | 1.1. Increased awareness 1.2. Higher school retention 1.3. Enforcement of laws | 1.1. KAP Surveys 1.2. School data 1.3a. Police reports 1.3b. Court Reports | Community cooperates; laws enforced |
| Outputs | - # awareness forums 1.2.1 # girls mentored 1.3.1 # trained local leaders | Activity Reports, Attendance Sheets | Regular participation by stakeholders |
| Activities | 1.1.1.a. Conduct forums 1.2.1a. Mentorship 1.3.1a. Train leaders | Program Reports, Photos, Records | Sufficient resources and trained staff |